AI SALES OS

EXECUTION PLAN v3.2

Apollo + Notion + Python + GitHub Actions

28 March 2026
Version 3.1 — Execution-First Approach

# Table of Contents

1    Project Overview & Current State

2    Architecture & Tech Stack

3    Scripts Inventory

4    Execution Plan — 4 Phases

4.1    Phase 1: ACTIVATE — Run What Exists

4.2    Phase 2: ACTION — Priority Engine

4.3    Phase 3: ENRICH — Signals Layer

4.4    Phase 4: OPTIMIZE — Score v2 + Odoo

5    Future Roadmap (Post-Data)

6    Decision Log

7    Risk Register

8    Notion Schema Reference

# 1. Project Overview & Current State

## What is AI Sales OS?

AI Sales OS is a unified sales intelligence platform that integrates Apollo.io (data source), Notion (CRM & operations hub), and Python automation (sync engine). The system ingests, scores, prioritizes, and takes action on 44,875 contacts and 15,407 companies — transforming raw data into revenue-generating actions.

## Current State Assessment

| Component | Status | Details |
| --- | --- | --- |
| Data Infrastructure | COMPLETE | 44,875 contacts + 15,407 companies in Notion |
| Apollo Integration | COMPLETE | MCP connected, API keys configured |
| Sync Engine v2.0 | BUILT — NOT RUN | 3 modes: incremental / backfill / full |
| Lead Score v1 | BUILT — NOT RUN | Formula ready, Notion field empty |
| Notion Views | CONFIGURED | HOT (>=80) / WARM (50-79) / COLD (<50) |
| GitHub Actions | OUTDATED | Workflow exists but uses old CLI syntax |
| Action Engine | NOT BUILT | No auto-task creation yet |
| Signals Layer | NOT BUILT | Job Postings + Job Change planned |
| Odoo Integration | NOT STARTED | Phase 4 — future |

CRITICAL INSIGHT: We have a production-grade data engine but zero revenue output. The #1 priority is running what exists, not building new features.

## Numbers: Plan v2.0 vs Reality

| Metric | Plan v2.0 (Original) | Actual Today | Growth |
| --- | --- | --- | --- |
| Companies | 3,606 | 15,407 | 4.3x |
| Contacts | 5,898 | 44,875 | 7.6x |
| Scripts Built | 2 | 10 | 5x |
| Sync Modes | 1 (basic) | 3 (incremental/backfill/full) | 3x |
| Lead Score | Formula only | Full script with CLI | Production-ready |
| Dedup Strategy | Apollo ID only | Triple dedup (ID + Email + seen_ids) | Enterprise-grade |

# 2. Architecture & Tech Stack

## System Architecture

The system follows a pipeline architecture with no external middleware dependencies:

APOLLO.IO  ------>  PYTHON SCRIPTS  ------>  NOTION

(Data Source)       (Sync Engine)            (CRM Hub)

daily_sync.py     ->  Contacts DB + Companies DB

lead_score.py     ->  Lead Score field

auto_tasks.py*    ->  Tasks (future)

job_postings.py*  ->  Company enrichment (future)

* = planned, not yet built

GITHUB ACTIONS  -->  Scheduled execution (daily cron)

CLAUDE (MCP)    -->  Analysis + manual operations

## Tech Stack

| Layer | Technology | Role |
| --- | --- | --- |
| Data Source | Apollo.io API | Contacts, companies, intent scores, job postings |
| CRM / Hub | Notion | Database, views, scoring, task management |
| Sync Engine | Python 3.11 | daily_sync.py, lead_score.py, helpers |
| Automation | GitHub Actions | Daily cron jobs, manual triggers |
| Analysis | Claude (MCP) | Ad-hoc analysis, planning, operations |
| Connectivity | Notion MCP + Apollo MCP | Direct API access from Claude |

## Key Design Decisions

No n8n / Make.com / Zapier: Python scripts on GitHub Actions provide the same automation with zero additional cost, full control, and no middleware to maintain.

Notion as CRM (not Salesforce/HubSpot): Notion provides flexibility for rapid iteration. We can add fields, views, and formulas instantly without admin overhead.

Embed Signals into existing schema: Instead of a separate Signals database, signal data (Job Postings, Job Change, Intent Trend) will be added as fields in the existing Companies and Contacts databases. This achieves 90% of the value at 30% of the complexity.

Lead Score v1 first, v2 later: Run the current formula (Intent + Engagement + Size + Seniority) first, evaluate the distribution, then iterate. Changing weights without data is theoretical optimization.

# 3. Scripts Inventory

All scripts are located in: CODE/Phase 3 - Sync/

| Script | Purpose | Status | CLI Usage |
| --- | --- | --- | --- |
| daily_sync.py | Apollo -> Notion sync (3 modes) | Ready — not run | python daily_sync.py --mode full |
| lead_score.py | Calculate Lead Score for all contacts | Ready — not run | python lead_score.py --force |
| notion_helpers.py | Shared Notion API utilities | Active | Imported by other scripts |
| sync_contacts.py | Legacy contact sync (v1) | Superseded by daily_sync.py | — |
| sync_companies.py | Legacy company sync (v1) | Superseded by daily_sync.py | — |
| initial_load_from_csv.py | One-time CSV import | Completed | — |
| verify_links.py | Verify contact-company links | Utility | python verify_links.py |
| webhook_server.py | Apollo webhook receiver | Experimental | python webhook_server.py |
| apollo_sync_scheduler.py | Legacy scheduler (v1) | Superseded | — |

## daily_sync.py — Sync Modes

| Mode | Description | Use Case | CLI |
| --- | --- | --- | --- |
| incremental | Pull records updated in last N hours/days | Daily automated sync | --mode incremental --hours 24 |
| backfill | Pull historical data with checkpoint resume | Fill gaps, recover from failures | --mode backfill --days 365 |
| full | Pull ALL records (alphabetical partitioning) | First-time full rebuild | --mode full |

## lead_score.py — Scoring Formula

| Component | Weight | Source | Range |
| --- | --- | --- | --- |
| Intent Score | 40% | Apollo Primary + Secondary Intent Score | 0-100 |
| Engagement | 35% | Email sent/opened/replied, meeting booked, outreach status | 0-100 |
| Company Size | 15% | Employee count from related Company | 0-100 |
| Seniority | 10% | Contact seniority field (C-suite=100 ... Intern=15) | 0-100 |

Final Score = (Intent x 0.45.*0.35.*0.10.*0.10)

# 4. Execution Plan — 4 Phases

This plan follows one principle: run what exists before building anything new. Each phase unlocks the next. No phase should be skipped.

| Phase | Name | Duration | Prerequisite | Key Output |
| --- | --- | --- | --- | --- |
| Phase 1 | ACTIVATE | 1-2 days | None | Lead Scores populated, views working |
| Phase 2 | ACTION | 3-5 days | Phase 1 complete + calibrated | Auto-tasks, priority engine |
| Phase 3 | ENRICH | 1 week | Phase 2 running | Job Postings, Job Change signals |
| Phase 4 | OPTIMIZE | 2 weeks | Signals data available | Lead Score v2, Odoo integration |

## 4.1  Phase 1: ACTIVATE — Run What Exists

PRIORITY: HIGHEST — This is the #1 task. Nothing else matters until this is done.

### Step 1: Update GitHub Actions Workflow

The current workflow uses the old --hours/--days syntax. It must be updated to use the new --mode syntax from daily_sync.py v2.1. Also add a lead_score.py step.

### Step 2: Run Full Sync

1. Ensure .env file has: APOLLO_API_KEY, NOTION_API_KEY, NOTION_DATABASE_ID_CONTACTS, NOTION_DATABASE_ID_COMPANIES

2. Run: python daily_sync.py --mode full

3. Expected duration: Several hours (44,875 contacts + 15,407 companies with API rate limits)

4. Monitor: tail -f daily_sync.log

5. Expected output: All Apollo records synced to Notion with latest data

### Step 3: Run Lead Score

1. Run: python lead_score.py --force

2. This calculates Lead Score for all 44,875 contacts

3. Monitor: tail -f lead_score.log

4. Expected output: Every contact has a Lead Score (0-100)

### Step 4: Calibration

After Lead Score runs, evaluate the distribution. This is critical — we need to verify the formula produces actionable results before building automation on top of it.

| Category | Score Range | Expected % | If Too High | If Too Low |
| --- | --- | --- | --- | --- |
| HOT | >= 80 | 0.5% - 2% | Tighten weights, raise thresholds | Lower intent weight or adjust seniority map |
| WARM | 50 - 79 | 10% - 20% | Check engagement scoring | Check if Intent Scores exist in data |
| COLD | < 50 | 80%+ | This is normal for cold Apollo data | Something is inflating scores |

WHY 80%+ COLD IS NORMAL: Most contacts are from Apollo with zero outreach history. Engagement score = 0 for all of them. Only contacts with high Intent Score AND high Seniority will score as HOT. This is expected and correct.

### Step 5: Activate GitHub Actions

1. Push updated code to GitHub repository

2. Add Secrets: APOLLO_API_KEY, NOTION_API_KEY, NOTION_DATABASE_ID_CONTACTS, NOTION_DATABASE_ID_COMPANIES

3. Update workflow to use --mode incremental for daily runs

4. Add lead_score.py as weekly job (recalculate scores after new data syncs)

5. Test: trigger manual workflow run from GitHub UI

### Phase 1 Success Criteria

| Criterion | Target | How to Verify |
| --- | --- | --- |
| Lead Score populated | 44,875 contacts scored | Notion filter: Lead Score is not empty |
| HOT leads identified | 200-900 contacts | HOT LEADS view count |
| WARM leads identified | 4,500-9,000 contacts | WARM LEADS view count |
| Daily sync active | Runs at 7 AM KSA daily | GitHub Actions history |
| Score distribution reviewed | Documented calibration results | This document updated |

## 4.2  Phase 2: ACTION — Priority Engine

GOAL: Convert Lead Score into revenue-generating actions. Every HOT lead should have a task assigned.

### What Needs to Be Built

A new script: auto_tasks.py — runs after lead_score.py, reads scored contacts from Notion, and creates follow-up tasks based on priority rules.

### Priority Rules

| Score Range | Priority | Action | Due Date | Task Title Template |
| --- | --- | --- | --- | --- |
| >= 80 (HOT) | CRITICAL | Call / Direct outreach | Same day | CALL: [Contact] at [Company] |
| 60-79 (WARM-HIGH) | HIGH | Personalized follow-up | Within 48 hours | FOLLOW-UP: [Contact] at [Company] |
| 50-59 (WARM) | MEDIUM | Add to nurture sequence | Within 1 week | NURTURE: [Contact] at [Company] |
| < 50 (COLD) | LOW | No action — monitor only | N/A | No task created |

### Design Questions to Resolve Before Building

1. Where do Tasks live? Do we need a new Notion database for Tasks, or use an existing one?

2. Who is the assignee? Single user, or round-robin across a team?

3. How to prevent duplicate tasks? If a HOT lead already has an open task, don't create another.

4. What triggers re-evaluation? When a contact's score changes, should the task priority update?

5. Notification mechanism? Email, Slack, or Notion notification only?

### Implementation Approach

Pure Python script using Notion MCP — no n8n, no Make.com, no external tools. The script will: (1) Query Notion for contacts with Lead Score >= 50, (2) Check if an open task exists for each contact, (3) Create new tasks following the priority rules, (4) Run on GitHub Actions after lead_score.py completes.

### Phase 2 Success Criteria

| Criterion | Target |
| --- | --- |
| auto_tasks.py built and tested | Script creates tasks correctly |
| HOT leads have tasks | 100% of Score >= 80 have an assigned task |
| WARM leads have tasks | 100% of Score >= 60 have a follow-up task |
| No duplicate tasks | Each contact has max 1 open task |
| GitHub Actions integrated | auto_tasks.py runs daily after sync + score |

## 4.3  Phase 3: ENRICH — Signals Layer

GOAL: Add real-time sales signals to improve scoring accuracy. Only signals available from Apollo API.

### Available Signals (Apollo API)

| Signal | Apollo Endpoint | Feasibility | Value | New Notion Fields |
| --- | --- | --- | --- | --- |
| Job Postings | organizations_job_postings | HIGH — direct endpoint | HIGH — hiring = growing = opportunity | Active Jobs Count, Last Job Posted, Hiring Departments |
| Job Change | Compare title/org between syncs | MEDIUM — build detection logic | HIGH — new role = new budget = outreach window | Job Changed (checkbox), Previous Title, Previous Company |
| Intent Trend | Compare Intent Score between syncs | HIGH — simple comparison | MEDIUM — rising intent = warming up | Intent Trend (Rising/Stable/Falling) |

### NOT Available from Apollo API

| Signal | Why Not Available | Alternative |
| --- | --- | --- |
| News / Events | No Apollo API endpoint for company news | Would need external source (Google News API, Crunchbase) — deferred |
| Email Engagement Detail | Open/click rates are internal Apollo data, not exposed via search API | We use checkbox fields (Email Opened, Replied) which are available |
| Buying Intent Scores | Already available as Intent Score — no separate 'buying intent' endpoint | Already captured in current Lead Score formula |

### Implementation Order

3A: Job Postings Enrichment (3 days)

1. Build job_postings_sync.py using apollo_organizations_job_postings endpoint

2. Add new fields to Notion Companies database: Active Jobs Count (number), Last Job Posted (date), Hiring Departments (multi-select)

3. Run on all companies with Apollo Organization ID

4. Schedule weekly on GitHub Actions (job postings don't change daily)

3B: Job Change Detection (2 days)

1. Add snapshot comparison logic to daily_sync.py

2. When a contact's title or organization changes between syncs: set Job Changed = true, save Previous Title and Previous Company

3. Add new fields to Notion Contacts database: Job Changed (checkbox), Previous Title (text), Previous Company (text), Job Change Date (date)

3C: Intent Trend Tracking (1 day)

1. Compare current Intent Score with previous score stored in daily_sync.py

2. Set Intent Trend field: Rising (increased by 10+), Falling (decreased by 10+), Stable (change < 10)

3. Add Intent Trend (select) field to Notion Contacts database

## 4.4  Phase 4: OPTIMIZE — Score v2 + Odoo

PREREQUISITE: Only start this phase after Signals data has been collected for at least 2 weeks.

### Lead Score v2 — Updated Formula

After signals data is available, update the scoring formula to include signals:

| Component | v1 Weight | v2 Weight | Change Reason |
| --- | --- | --- | --- |
| Intent Score | 40% | 30% | Reduced to make room for Signals |
| Engagement | 35% | 25% | Reduced slightly |
| Signals | 0% | 25% | NEW: Job Change (+20), Job Postings (+5-15), Intent Rising (+10) |
| Company Size | 15% | 10% | Slight reduction |
| Seniority | 10% | 10% | Unchanged |

IMPORTANT: Do NOT change weights until we have real signals data. Giving 25% weight to signals when all signal values are zero will weaken the overall score.

### Odoo Integration

Once the pipeline is generating qualified opportunities, integrate with Odoo for revenue tracking:

1. Map Notion Opportunity fields to Odoo CRM Pipeline

2. Build odoo_sync.py for bi-directional sync

3. Sync: Opportunity Name, Company, Contact, Value, Stage, Close Date

4. Set up Odoo webhooks for stage changes (Odoo -> Notion)

5. Revenue dashboard in Odoo for financial reporting

# 5. Future Roadmap (Post-Data)

These items are documented for future reference. They should NOT be started until all 4 phases are complete and generating revenue. Documenting them now ensures nothing is forgotten.

| Item | Description | Prerequisite | Estimated Effort | Priority |
| --- | --- | --- | --- | --- |
| Claude AI Analysis Layer | Automated analysis of lead patterns, weekly insights reports, anomaly detection in scoring | 6+ weeks of Lead Score data | 1 week | LOW — after Phase 4 |
| Advanced Engagement Tracking | Track email sequence performance, A/B test results, response time analysis | Apollo Sequences actively running | 3 days | MEDIUM — when outreach starts |
| News/Events Integration | Monitor company news via external APIs (Google News, Crunchbase) | Proven ROI from existing signals | 1 week | LOW — external API dependency |
| Multi-User Task Assignment | Round-robin task assignment, workload balancing, team performance metrics | Sales team > 1 person | 3 days | MEDIUM — when team grows |
| Notion Automations (Native) | Trigger notifications on Lead Score changes, new HOT leads | Phase 2 complete | 1 day | MEDIUM |
| Custom Dashboard (HTML) | Live dashboard showing pipeline metrics, scoring distribution, signal activity | 3+ months of data | 1 week | LOW — nice to have |
| Apollo Sequence Integration | Auto-add HOT leads to Apollo email sequences via API | Sequences designed and tested manually | 2 days | HIGH — after Phase 2 |
| Competitor Monitoring | Track competitor mentions, technology changes in target accounts | External data source needed | 1 week | LOW |

# 6. Decision Log

This section documents key architectural and strategic decisions made during project planning. Each decision includes the reasoning so future contributors understand the context.

| Date | Decision | Reasoning | Status |
| --- | --- | --- | --- |
| 27 Mar 2026 | No n8n / Make.com | We already have Python + GitHub Actions + Notion MCP + Apollo MCP. Adding middleware introduces cost, complexity, and a dependency with no incremental value. Python scripts give full control. | FINAL |
| 27 Mar 2026 | Embed signals in existing schema | The original proposal was a separate Signals database in Notion. Rejected because: (1) adds a 3rd database to maintain, (2) creates confusion between Signal Score and Lead Score, (3) 90% of the value comes from adding fields to existing tables. | FINAL |
| 27 Mar 2026 | Lead Score v1 before v2 | Don't change scoring weights until signals data exists. Giving 25% weight to zero-value fields weakens the formula. Run v1, evaluate distribution, then iterate. | FINAL |
| 27 Mar 2026 | Run existing code before new features | daily_sync.py and lead_score.py are built but never executed. Any new development (signals, AI, dashboards) before running these is a distraction. | FINAL |
| 27 Mar 2026 | 4 phases, not 7 | The original proposal had 7 phases. Reduced to 4 because multiple 'phases' were actually steps within a single day's work. Phase inflation creates illusion of progress. | FINAL |
| 27 Mar 2026 | 80%+ COLD is expected | For cold Apollo data with no outreach history, most contacts will score low. This is correct behavior, not a bug. Calibration should validate this, not 'fix' it. | FINAL |
| 27 Mar 2026 | No Claude AI integration yet | Claude integration (automated analysis, decision augmentation) is valuable but premature. Need real data flowing first. Deferred to post-Phase 4. | REVISIT after Phase 4 |
| 27 Mar 2026 | GitHub Actions as scheduler | Instead of a separate scheduling service, GitHub Actions runs daily cron. Free tier is sufficient. Workflow needs updating to match daily_sync.py v2.1 CLI. | FINAL |

# 7. Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Full Sync fails mid-run (API limits, timeouts) | MEDIUM | HIGH | Backfill mode has checkpoint resume. Monitor logs. Time-window splitting handles 50K pagination limit. |
| Lead Score distribution is skewed | MEDIUM | MEDIUM | Calibration phase evaluates distribution. Adjust weights or thresholds if needed. Expected: 80%+ COLD. |
| Apollo API rate limiting | LOW | MEDIUM | Built-in rate_limiter in notion_helpers.py. MAX_WORKERS=3 limits concurrency. Exponential backoff on 429 errors. |
| Notion API rate limiting | LOW | MEDIUM | rate_limiter function with delay between requests. Batch operations where possible. |
| Duplicate records in Notion | LOW | HIGH | Triple dedup strategy: Apollo ID + Email + seen_ids set. Pre-loading all Notion records before sync. |
| GitHub Actions fails silently | LOW | MEDIUM | Workflow has failure notification step. Logs uploaded as artifacts. Manual trigger available. |
| Stale data after long downtime | LOW | LOW | Use backfill mode to catch up. Checkpoint system resumes from last successful point. |
| Odoo integration complexity | MEDIUM | MEDIUM | Deferred to Phase 4. Will evaluate API capabilities before committing to bi-directional sync. |

# 8. Notion Schema Reference

## Contacts Database — Key Fields

| Field | Type | Source | Status |
| --- | --- | --- | --- |
| Name | title | Apollo | Populated |
| Email | email | Apollo | Populated (95.7%+) |
| Apollo Contact ID | text | Apollo | Populated (unique) |
| Company (relation) | relation | Notion linking | Populated |
| Lead Score | number | lead_score.py | EMPTY — Phase 1 |
| Primary Intent Score | number | Apollo | Populated |
| Secondary Intent Score | number | Apollo | Populated |
| Seniority | select | Apollo | Populated |
| Outreach Status | select | Manual / Apollo | Partial |
| Reply Status | select | Manual | Partial |
| Email Sent / Opened / Replied | checkbox | Apollo | Populated |
| Meeting Booked | checkbox | Manual | Partial |
| Demoed | checkbox | Manual | Partial |
| Qualification Status | select | Manual | Partial |
| Stage | select | Manual | Partial |
| Job Changed* | checkbox | daily_sync.py | PLANNED — Phase 3 |
| Previous Title* | text | daily_sync.py | PLANNED — Phase 3 |
| Intent Trend* | select | daily_sync.py | PLANNED — Phase 3 |

## Companies Database — Key Fields

| Field | Type | Source | Status |
| --- | --- | --- | --- |
| Company Name | title | Apollo | Populated |
| Apollo Account ID | text | Apollo | Populated (unique) |
| Domain | url | Apollo | Populated |
| Employee Count | number | Apollo | Populated |
| Industry | select | Apollo | Populated |
| Contacts (relation) | relation | Notion linking | Populated |
| Active Jobs Count* | number | job_postings_sync.py | PLANNED — Phase 3 |
| Last Job Posted* | date | job_postings_sync.py | PLANNED — Phase 3 |
| Hiring Departments* | multi-select | job_postings_sync.py | PLANNED — Phase 3 |

## Notion Views

| View | Filter | Purpose |
| --- | --- | --- |
| HOT LEADS | Lead Score >= 80 | Immediate outreach targets |
| WARM LEADS | Lead Score >= 50 AND < 80 | Nurture and follow-up |
| COLD LEADS | Lead Score < 50 | Monitor only |

* Fields marked with asterisk are planned additions for Phase 3. They need to be created in Notion before the corresponding scripts can populate them.

# Timeline Summary

| Week | Phase | Key Actions | Deliverable |
| --- | --- | --- | --- |
| Week 1 | Phase 1: ACTIVATE | Full Sync + Lead Score + Calibration + GitHub Actions | 44,875 scored leads, daily sync running |
| Week 2-3 | Phase 2: ACTION | Build auto_tasks.py + priority rules + integrate with GH Actions | Every HOT/WARM lead has an assigned task |
| Week 3-4 | Phase 3: ENRICH ✔ COMPLETE | Job Postings Intent + Auto Sequences + Analytics + Calibrator | 16-step pipeline active. Sequences running. Engagement syncing. |
| Week 4 (Mar 2026) | Phase 3.5: MEET ✔ COMPLETE | Meeting Intelligence: meeting_tracker + meeting_analyzer + opportunity_manager | Meetings → Opportunities. Revenue loop closes. 17 scripts total. |
| Week 5-8 | Phase 4: OPTIMIZE | Lead Score v2 + Odoo integration | Revenue tracking, pipeline management |

Document Version: 3.2  |  Date: 28 March 2026  |  Phase 3.5: COMPLETE  |  Status: ACTIVE