## Setup Tracking
🗄️ NOTION SETUP TRACKER
Project: | AI Sales OS - Phase 1B
Status: | In Progress
Date Started: | March 24, 2026
Database | Total Fields | Fields Added | % Complete | Views | Relations | Status | Notes
Companies | 28 | 0 |  | 4 | 3 | pending | Primary database
Contacts | 38 | 0 |  | 8 | 1 | pending | Lead scoring data
Opportunities | 26 | 0 |  | 5 | 2 | pending | Pipeline tracking
Tasks | 23 | 0 |  | 6 | 3 | pending | Task management
Meetings | 18 | 0 |  | 4 | 3 | pending | Meeting logs
SETUP SUMMARY
Total Databases: | 5
Total Fields:
Total Views:
Total Relations:
Overall Progress:
FIELD SETUP CHECKLIST
☐ | Create Companies database
☐ | Add Companies fields (28)
☐ | Create Companies views (4)
☐ | Create Contacts database
☐ | Add Contacts fields (38)
☐ | Create Contacts views (8)
☐ | Create Opportunities database
☐ | Add Opportunities fields (26)
☐ | Create Opportunities views (5)
☐ | Create Tasks database
☐ | Add Tasks fields (23)
☐ | Create Tasks views (6)
☐ | Create Meetings database
☐ | Add Meetings fields (18)
☐ | Create Meetings views (4)
☐ | Set up all Relations
☐ | Test Relations between databases
☐ | Verify Views work correctly
TIMELINE & DEPENDENCIES
Phase 1: Create Databases | Day 1-2 | Companies, Contacts, Opportunities
Phase 2: Create Tasks & Meetings | Day 3 | Tasks, Meetings databases
Phase 3: Set up Relations | Day 3-4 | Link all databases
Phase 4: Create Views | Day 4-5 | All views and filters
Phase 5: Test & Verify | Day 5 | Full QA checklist